## Summary
Item |  | Details |  |  |  | Article
Title of Contract |  | An eLearning Platform for a Knowledge Europe |  |  |  | Article 1
ACRONYM |  | eLearning Europe |  |  |  | Article 1
Contract Number |  | 500135 |  |  |  | Top of first page
Type of Contract |  | Integrated Project |  |  |  | Top of first page
Estimated Cost
EC Contribution |  | 15000000 |  |  |  | Article 5
Start Date |  | 1.1.2004 |  |  |  | Article 4.2
Duration |  | 60 months |  |  |  | Article 4.2
End date |  | 31.12.2008 |  |  |  | Calculation
Contract Signed (Start of Contract) |  | Assume 1/2/2004 |  |  |  | Article 2.1
Form As signed |  | Latest Date 1/2/2004 + 60 |  | 2004-04-01 |  | Article 2.1
Period 1 |  | 1.1.2004 to 31/12/2004 |  |  |  | Article 6
Period 2 |  | 1.1.2005 to 31/12/2005 |  |  |  | Article 6
Period 3 |  | 1.1.2006 to 31/12/2006 |  |  |  | Article 6
Period 4 |  | 1.1.2007 to 31/12/2007 |  |  |  | Article 6
Period 5 |  | 1.1.2008 to 31/12/2008 |  |  |  | Article 6
Item | Details |  | Earliest date |  | Days to complete |  | Article in Contract
END OF YEAR 1 | [7 empty] | 0
Report | Periodic activity report’ |  | 2004-12-31 |  | + 45 days |  | Article II.7.2.a | 1
Report | Dissemination + use plan’ |  | 31/12/2004 |  | + 45 days |  | Article II.7.2.a | 2
Report | Management report |  | 31/12/2004 |  | + 45 days |  | Article II.7.2.b | 3
Report | Justification of resources |  | 31/12/2004 |  | + 45 days |  | Article II.7.2.b (i) | 4
Report | Form C |  | 31/12/2004 |  | + 45 days |  | Article II.7.2.b (ii) | 5
Report | Summary financial report |  | 31/12/2004 |  | + 45 days |  | Article II.7.2.b (iii) | 6
Report | Distribution of funds |  | 31/12/2004 |  | + 45 days |  | Article II.7.2.c | 7
Report | Supplementary reports |  | 31/12/2004 |  | + 45 days |  | Article II.7.2.3 | 8
Cert | Audit Certificate per partner ? |  | 31/12/2004 |  | + 45 days |  | Article II.7.3 and II.26 | 9
Report | 18 month implementation plan |  | 31/12/2004 |  | + 45 days |  | Article III.2 | 10
Report | JRC Share of Payment |  | 31/12/2004 |  | + 45 days |  | Article 9 (c) | 11
END OF YEAR 2 | [7 empty] | 0
Report | Periodic activity report’ |  | 31/12/2005 |  | + 45 days |  | Article II.7.2.a | 1
Report | Dissemination + use plan’ |  | 31/12/2005 |  | + 45 days |  | Article II.7.2.a | 2
Report | Management report |  | 31/12/2005 |  | + 45 days |  | Article II.7.2.b | 3
Report | Justification of resources |  | 31/12/2005 |  | + 45 days |  | Article II.7.2.b (i) | 4
Report | Form C |  | 31/12/2005 |  | + 45 days |  | Article II.7.2.b (ii) | 5
Report | Summary financial report |  | 31/12/2005 |  | + 45 days |  | Article II.7.2.b (iii) | 6
Report | Distribution of funds |  | 31/12/2005 |  | + 45 days |  | Article II.7.2.c | 7
Report | Supplementary reports |  | 31/12/2005 |  | + 45 days |  | Article II.7.2.3 | 8
Cert | Audit Certificate per partner |  | 31/12/2005 |  | + 45 days |  | Article II.7.3 and II.26 | 9
Report | 18 month implementation plan |  | 31/12/2005 |  | + 45 days |  | Article III.2 | 10
Report | JRC Share of Payment |  | 2005-12-31 |  | + 45 days |  | Article 9 (c) | 10
END OF YEAR 3 | [7 empty] | 11
Report | Periodic activity report’ |  | 31/12/2006 |  | + 45 days |  | Article II.7.2.a | 1
Report | Dissemination +use plan’ |  | 31/12/2006 |  | + 45 days |  | Article II.7.2.a | 2
Report | Management report |  | 31/12/2006 |  | + 45 days |  | Article II.7.2.b | 3
Report | Justification of resources |  | 31/12/2006 |  | + 45 days |  | Article II.7.2.b (i) | 4
Report | Form C |  | 31/12/2006 |  | + 45 days |  | Article II.7.2.b (ii) | 5
Report | Summary financial report |  | 31/12/2006 |  | + 45 days |  | Article II.7.2.b (iii) | 6
Report | Distribution of funds |  | 31/12/2006 |  | + 45 days |  | Article II.7.2.c | 7
Report | Supplementary reports |  | 31/12/2006 |  | + 45 days |  | Article II.7.2.3 | 8
Cert | Audit Certificate per partner |  | 31/12/2006 |  | + 45 days |  | Article II.7.3 and II.26 | 9
Report | 18 month implementation plan |  | 31/12/2006 |  | + 45 days |  | Article III.2 | 10
Report | JRC Share of Payment |  | 2006-12-31 |  | + 45 days |  | Article 9 (c) | 11
END OF YEAR 4 | [7 empty] | 0
Report | Periodic activity report’ |  | 31/12/2007 |  | + 45 days |  | Article II.7.2.a | 1
Report | Dissemination +use plan’ |  | 31/12/2007 |  | + 45 days |  | Article II.7.2.a | 2
Report | Management report |  | 31/12/2007 |  | + 45 days |  | Article II.7.2.b | 3
Report | Justification of resources |  | 31/12/2007 |  | + 45 days |  | Article II.7.2.b (i) | 4
Report | Form C |  | 31/12/2007 |  | + 45 days |  | Article II.7.2.b (ii) | 5
Report | Summary financial report |  | 31/12/2007 |  | + 45 days |  | Article II.7.2.b (iii) | 6
Report | Distribution of funds |  | 31/12/2007 |  | + 45 days |  | Article II.7.2.c | 7
Report | Supplementary reports |  | 31/12/2007 |  | + 45 days |  | Article II.7.2.3 | 8
Cert | Audit Certificate per partner |  | 31/12/2007 |  | + 45 days |  | Article II.7.3 and II.26 | 9
Report | 12 mon. implementation plan |  | 31/12/2007 |  | + 45 days |  | Article III.2 | 10
Report | JRC Share of Payment |  | 2007-12-31 |  | + 45 days |  | Article 9 (c) | 11
END OF YEAR 5 | [7 empty] | 0
Report | Periodic activity report’ |  | 31/12/2008 |  | + 45 days |  | Article II.7.2.a | 1
Report | Dissemination+use plan’ |  | 31/12/2008 |  | + 45 days |  | Article II.7.2.a | 2
Report | Management report |  | 31/12/2008 |  | + 45 days |  | Article II.7.2.b | 3
Report | Justification of resources |  | 31/12/2008 |  | + 45 days |  | Article II.7.2.b (i) | 4
Report | Form C |  | 31/12/2008 |  | + 45 days |  | Article II.7.2.b (ii) | 5
Report | Summary financial report |  | 31/12/2008 |  | + 45 days |  | Article II.7.2.b (iii) | 6
Report | Distribution of funds |  | 31/12/2008 |  | + 45 days |  | Article II.7.2.c | 7
Report | Supplementary reports |  | 31/12/2008 |  | + 45 days |  | Article II.7.2.3 | 8
Cert | Audit Certificate per partner |  | 31/12/2008 |  | + 45 days |  | Article II.7.3 and II.26 | 9
Report | JRC Share of Payment |  | 2008-12-31 |  | + 45 days |  | Article 9 (c) | 11
END OF PROJECT | [7 empty] | 0
Final Report | Periodic activity report’ |  | 31/12/2008 |  | + 45 days |  | Article II.7.4.a | 1
Final Report | Dissemination + use plan’ |  | 31/12/2008 |  | + 45 days |  | Article II.7.4.a | 2
Final Report | Management report |  | 31/12/2008 |  | + 45 days |  | Article II.7.2.b | 3
Final Report | Justification of resources |  | 31/12/2008 |  | + 45 days |  | Article II.7.2.b (i) | 4
Final Report | Summary financial report |  | 31/12/2008 |  | + 45 days |  | Article II.7.2.b (iii) | 6
Final Report | Distribution of funds |  | 2009-06-30 |  | + 45 days |  | Article II.7.2.c | 7
Final Report | Supplementary reports |  | 31/12/2008 |  | + 45 days |  | Article II.7.2.3 | 8
PAYMENTS
Payment | Advance for first 18 months (Plan 1) |  | 2004-05-15 |  | 4000000 |  | Article 8.2.a Core
Payment | Advance for second 18 months(Plan 2) |  | 2005-06-30 |  | 4400000 |  | Article 8.2.a Core | 1
Payment | Balance of year 1 |  | 2005-06-30 |  | -1000000 |  | Article 8.2.b Core | 2
Payment | Advance Plan 2-balance year 1 |  | 30/04/2005 |  | 3400000 |  | Article 8.2.b Core | 3
Payment | Advance next 18 months(Plan 3) |  | 2006-06-30 |  | 3200000 |  | Article 8.2.a Core | 1
Payment | Balance of year 2 |  | 2006-06-30 |  | -400000 |  | Article 8.2.b Core | 2
Payment | Advance 3-Balance Year 2 |  | 2006-06-30 |  | 2800000 |  | Article 8.2.b Core | 3
Payment | Advance next 18 months(Plan 4) |  | 2007-06-30 |  | 2800000 |  | Article 8.2.a Core | 1
Payment | Balance of year 3 |  | 2007-06-30 |  | -200000 |  | Article 8.2.b Core | 2
Payment | Advance 4-Balance Year 3 |  | 2007-06-30 |  | 2600000 |  | Article 8.2.b Core | 3
Payment | Advance for last 12 months |  | 2008-06-30 |  | 2400000 |  | Article 8.2.a Core | 1
Payment | Balance of year 4 |  | 2008-06-30 |  | -800000 |  | Article 8.2.b Core | 2
Payment | Advance 5-Balance Year 4 |  | 2008-06-30 |  | 1600000 |  | Article 8.2.b Core | 3
Payment | Final Payment |  | 2009-06-30 |  | 600000 |  | Article 8.2.a Core | 1
DELIVERABLES
Deliverable | Website |  | 30/6/2004 |  | D1 |  | Technical Annex
Deliverable | Specification of software |  | 31/8/2004 |  | D2 |  | Technical Annex
Deliverable | Rapid prototyping of software |  | 31/12/2004 |  | D3 |  | Technical Annex
Deliverable | Testing prototype software |  | 28/2/2005 |  | D4 |  | Technical Annex
Deliverable | Revision of specification |  | 16/12/2005 |  | D5 |  | Technical Annex
Deliverable | Design specification |  | 30/6/3005 |  | D6 |  | Technical Annex
REVIEWS
Review | Review of Year 1 |  | 1/4/2005 |  |  |  | Article II.7
Review | Review of Year2 + mid term |  | 1/4/2006 |  |  |  | Article II.7 + 9.2
Review | Review of Year 3 |  | 1/4/2007 |  |  |  | Article II.7
Review | Review of Year 4 |  | 1/4/2008 |  |  |  | Article II.7
Review | Final Review |  | 15/12/2008
SPECIAL CLAUSE (CLUSTER MEETINGS)
Cluster | Cluster Meeting Year 1 |  | 1/6/2004 |  |  |  | Article 9.1
Cluster | Cluster Meeting Year 2 |  | 1/6/2005 |  |  |  | Article 9.1
Cluster | Cluster Meeting Year 3 |  | 1/6/2006 |  |  |  | Article 9.1
Cluster | Cluster Meeting Year 4 |  | 1/6/2007 |  |  |  | Article 9.1
Cluster | Cluster Meeting Year 5 |  | 1/6/2008 |  |  |  | Article 9.1
END OF AUDIT PERIOD
Audit | End of Audit Period |  | 2013-12-31

## Deadlines
Item | Details | Earliest date | Days to complete | Article in Contract
Report | Periodic activity report’ | 2004-12-31 | + 45 days | Article II.7.2.a | 1
Report | Dissemination + use plan’ | 31/12/2004 | + 45 days | Article II.7.2.a | 2
Report | Management report | 31/12/2004 | + 45 days | Article II.7.2.b | 3
Report | Justification of resources | 31/12/2004 | + 45 days | Article II.7.2.b (i) | 4
Report | Form C | 31/12/2004 | + 45 days | Article II.7.2.b (ii) | 5
Report | Summary financial report | 31/12/2004 | + 45 days | Article II.7.2.b (iii) | 6
Report | Distribution of funds | 31/12/2004 | + 45 days | Article II.7.2.c | 7
Report | Supplementary reports | 31/12/2004 | + 45 days | Article II.7.2.d | 8
Cert | Audit Certificate per partner ? | 31/12/2004 | + 45 days | Article II.26 | 9
Report | 18 month implementation plan | 31/12/2004 | + 45 days | Article III.2 | 10
Report | JRC Share of Payment | 31/12/2004 | + 45 days | Article 9 (c) | 11
Report | Periodic activity report’ | 31/12/2005 | + 45 days | Article II.7.2.a | 1
Report | Dissemination + use plan’ | 31/12/2005 | + 45 days | Article II.7.2.a | 2
Report | Management report | 31/12/2005 | + 45 days | Article II.7.2.b | 3
Report | Justification of resources | 31/12/2005 | + 45 days | Article II.7.2.b (i) | 4
Report | Form C | 31/12/2005 | + 45 days | Article II.7.2.b (ii) | 5
Report | Summary financial report | 31/12/2005 | + 45 days | Article II.7.2.b (iii) | 6
Report | Distribution of funds | 31/12/2005 | + 45 days | Article II.7.2.c | 7
Report | Supplementary reports | 31/12/2005 | + 45 days | Article II.7.2.d | 8
Cert | Audit Certificate per partner | 31/12/2005 | + 45 days | Article II.26 | 9
Report | 18 month implementation plan | 31/12/2005 | + 45 days | Article III.2 | 10
Report | JRC Share of Payment | 2005-12-31 | + 45 days | Article 9 (c) | 10
Report | Periodic activity report’ | 31/12/2006 | + 45 days | Article II.7.2.a | 1
Report | Dissemination +use plan’ | 31/12/2006 | + 45 days | Article II.7.2.a | 2
Report | Management report | 31/12/2006 | + 45 days | Article II.7.2.b | 3
Report | Justification of resources | 31/12/2006 | + 45 days | Article II.7.2.b (i) | 4
Report | Form C | 31/12/2006 | + 45 days | Article II.7.2.b (ii) | 5
Report | Summary financial report | 31/12/2006 | + 45 days | Article II.7.2.b (iii) | 6
Report | Distribution of funds | 31/12/2006 | + 45 days | Article II.7.2.c | 7
Report | Supplementary reports | 31/12/2006 | + 45 days | Article II.7.2.d | 8
Cert | Audit Certificate per partner | 31/12/2006 | + 45 days | Article II.26 | 9
Report | 18 month implementation plan | 31/12/2006 | + 45 days | Article III.2 | 10
Report | JRC Share of Payment | 2006-12-31 | + 45 days | Article 9 (c) | 11
Report | Periodic activity report’ | 31/12/2007 | + 45 days | Article II.7.2.a | 1
Report | Dissemination +use plan’ | 31/12/2007 | + 45 days | Article II.7.2.a | 2
Report | Management report | 31/12/2007 | + 45 days | Article II.7.2.b | 3
Report | Justification of resources | 31/12/2007 | + 45 days | Article II.7.2.b (i) | 4
Report | Form C | 31/12/2007 | + 45 days | Article II.7.2.b (ii) | 5
Report | Summary financial report | 31/12/2007 | + 45 days | Article II.7.2.b (iii) | 6
Report | Distribution of funds | 31/12/2007 | + 45 days | Article II.7.2.c | 7
Report | Supplementary reports | 31/12/2007 | + 45 days | Article II.7.2.d | 8
Cert | Audit Certificate per partner | 31/12/2007 | + 45 days | Article II.26 | 9
Report | 18 mon. implementation plan | 31/12/2007 | + 45 days | Article III.2 | 10
Report | JRC Share of Payment | 2007-12-31 | + 45 days | Article 9 (c) | 11
Report | Periodic activity report’ | 31/12/2008 | + 45 days | Article II.7.2.a | 1
Report | Dissemination+use plan’ | 31/12/2008 | + 45 days | Article II.7.2.a | 2
Report | Management report | 31/12/2008 | + 45 days | Article II.7.2.b | 3
Report | Justification of resources | 31/12/2008 | + 45 days | Article II.7.2.b (i) | 4
Report | Form C | 31/12/2008 | + 45 days | Article II.7.2.b (ii) | 5
Report | Summary financial report | 31/12/2008 | + 45 days | Article II.7.2.b (iii) | 6
Report | Distribution of funds | 31/12/2008 | + 45 days | Article II.7.2.c | 7
Report | Supplementary reports | 31/12/2008 | + 45 days | Article II.7.2.d | 8
Cert | Audit Certificate per partner | 31/12/2008 | + 45 days | Article II.26 | 9
Report | 18 month implementation plan | 31/12/2008 | + 45 days | Article III.2 | 10
Report | JRC Share of Payment | 2008-12-31 | + 45 days | Article 9 (c) | 11
Final Report | Periodic activity report’ | 31/12/2008 | + 45 days | Article II.7.4.a | 1
Final Report | Dissemination + use plan’ | 31/12/2008 | + 45 days | Article II.7.4.a | 2
Final Report | Management report | 31/12/2008 | + 45 days | Article II.7.4.b | 3
Final Report | Summary financial report | 31/12/2008 | + 45 days | Article II.7.4.b (iii) | 6
Final Report | Supplementary reports | 2008-12-31 | + 45 days | Article II.7.4.c | 8
Final Report | Distribution of funds | 2009-06-30 | + 45 days | Article II.7.4.d | 7
Payment | Advance for first 18 months (Plan 1) | 2004-05-15 | 4000000 | Article 8.2.a Core
Payment | Advance for second 18 months(Plan 2) | 2005-06-30 | 4400000 | Article 8.2.a Core | 1
Payment | Balance of year 1 | 2005-06-30 | -1000000 | Article 8.2.b Core | 2
Payment | Advance Plan 2-balance year 1 | 30/04/2005 | 3400000 | Article 8.2.b Core | 3
Payment | Advance next 18 months(Plan 3) | 2006-06-30 | 3200000 | Article 8.2.a Core | 1
Payment | Balance of year 2 | 2006-06-30 | -400000 | Article 8.2.b Core | 2
Payment | Advance 3-Balance Year 2 | 2006-06-30 | 2800000 | Article 8.2.b Core | 3
Payment | Advance next 18 months(Plan 4) | 2007-06-30 | 2800000 | Article 8.2.a Core | 1
Payment | Balance of year 3 | 2007-06-30 | -200000 | Article 8.2.b Core | 2
Payment | Advance 4-Balance Year 3 | 2007-06-30 | 2600000 | Article 8.2.b Core | 3
Payment | Advance for last 12 months | 2008-06-30 | 2400000 | Article 8.2.a Core | 1
Payment | Balance of year 4 | 2008-06-30 | -800000 | Article 8.2.b Core | 2
Payment | Advance 5-Balance Year 4 | 2008-06-30 | 1600000 | Article 8.2.b Core | 3
Payment | Final Payment | 2009-06-30 | 600000 | Article 8.2.a Core | 1
Deliverable | Website | 30/6/2004 | D1 | Technical Annex
Deliverable | Specification of software | 31/8/2004 | D2 | Technical Annex
Deliverable | Rapid prototyping of software | 31/12/2004 | D3 | Technical Annex
Deliverable | Testing prototype software | 28/2/2005 | D4 | Technical Annex
Deliverable | Revision of specification | 16/12/2005 | D5 | Technical Annex
Deliverable | Design specification | 30/6/3005 | D6 | Technical Annex
Review | Review of Year 1 | 1/4/2005 |  | Article II.7
Review | Review of Year2 + mid term | 1/4/2006 |  | Article II.7 + 9.2
Review | Review of Year 3 | 1/4/2007 |  | Article II.7
Review | Review of Year 4 | 1/4/2008 |  | Article II.7
Review | Final Review | 15/12/2008
Cluster | Cluster Meeting Year 1 | 1/6/2004 |  | Article 9.1
Cluster | Cluster Meeting Year 2 | 1/6/2005 |  | Article 9.1
Cluster | Cluster Meeting Year 3 | 1/6/2006 |  | Article 9.1
Cluster | Cluster Meeting Year 4 | 1/6/2007 |  | Article 9.1
Cluster | Cluster Meeting Year 5 | 1/6/2008 |  | Article 9.1
Audit | End of Audit Period | 31/12/2011

## Sorted
Item | Details | Earliest date | Days to complete | Article in Contract
Report | Periodic activity report’ | 2004-12-31 | + 45 days | Article II.7.2.a | 1
Payment | Advance for first 18 months (Plan 1) | 2004-05-15 | 4000000 | Article 8.2.a Core
Cluster | Cluster Meeting Year 1 | 1/6/2004 |  | Article 9.1
Deliverable | Website | 30/6/2004 | D1 | Technical Annex
Deliverable | Specification of software | 31/8/2004 | D2 | Technical Annex
Report | Dissemination + use plan’ | 31/12/2004 | + 45 days | Article II.7.2.a | 2
Report | Management report | 31/12/2004 | + 45 days | Article II.7.2.b | 3
Report | Justification of resources | 31/12/2004 | + 45 days | Article II.7.2.b (i) | 4
Report | Form C | 31/12/2004 | + 45 days | Article II.7.2.b (ii) | 5
Report | Summary financial report | 31/12/2004 | + 45 days | Article II.7.2.b (iii) | 6
Report | Distribution of funds | 31/12/2004 | + 45 days | Article II.7.2.c | 7
Report | Supplementary reports | 31/12/2004 | + 45 days | Article II.7.2.d | 8
Cert | Audit Certificate per partner ? | 31/12/2004 | + 45 days | Article II.26 | 9
Report | 18 month implementation plan | 31/12/2004 | + 45 days | Article III.2 | 10
Report | JRC Share of Payment | 31/12/2004 | + 45 days | Article 9 (c) | 11
Deliverable | Rapid prototyping of software | 31/12/2004 | D3 | Technical Annex
Deliverable | Testing prototype software | 28/2/2005 | D4 | Technical Annex
Review | Review of Year 1 | 1/4/2005 |  | Article II.7
Cluster | Cluster Meeting Year 2 | 1/6/2005 |  | Article 9.1
Payment | Advance for second 18 months(Plan 2) | 2005-06-30 | 4400000 | Article 8.2.a Core | 1
Payment | Balance of year 1 | 2005-06-30 | -1000000 | Article 8.2.b Core | 2
Payment | Advance Plan 2-balance year 1 | 2005-06-30 | 3400000 | Article 8.2.b Core | 3
Deliverable | Design specification | 2005-06-30 | D6 | Technical Annex
Deliverable | Revision of specification | 16/12/2005 | D5 | Technical Annex
Report | Periodic activity report’ | 31/12/2005 | + 45 days | Article II.7.2.a | 1
Report | Dissemination + use plan’ | 31/12/2005 | + 45 days | Article II.7.2.a | 2
Report | Management report | 31/12/2005 | + 45 days | Article II.7.2.b | 3
Report | Justification of resources | 31/12/2005 | + 45 days | Article II.7.2.b (i) | 4
Report | Form C | 31/12/2005 | + 45 days | Article II.7.2.b (ii) | 5
Report | Summary financial report | 31/12/2005 | + 45 days | Article II.7.2.b (iii) | 6
Report | Distribution of funds | 31/12/2005 | + 45 days | Article II.7.2.c | 7
Report | Supplementary reports | 31/12/2005 | + 45 days | Article II.7.2.d | 8
Cert | Audit Certificate per partner | 31/12/2005 | + 45 days | Article II.26 | 9
Report | 18 month implementation plan | 31/12/2005 | + 45 days | Article III.2 | 10
Report | JRC Share of Payment | 2005-12-31 | + 45 days | Article 9 (c) | 10
Review | Review of Year2 + mid term | 1/4/2006 |  | Article II.7 + 9.2
Cluster | Cluster Meeting Year 3 | 1/6/2006 |  | Article 9.1
Payment | Advance next 18 months(Plan 3) | 2006-06-30 | 3200000 | Article 8.2.a Core | 1
Payment | Balance of year 2 | 2006-06-30 | -400000 | Article 8.2.b Core | 2
Payment | Advance 3-Balance Year 2 | 2006-06-30 | 2800000 | Article 8.2.b Core | 3
Report | Periodic activity report’ | 31/12/2006 | + 45 days | Article II.7.2.a | 1
Report | Dissemination +use plan’ | 31/12/2006 | + 45 days | Article II.7.2.a | 2
Report | Management report | 31/12/2006 | + 45 days | Article II.7.2.b | 3
Report | Justification of resources | 31/12/2006 | + 45 days | Article II.7.2.b (i) | 4
Report | Form C | 31/12/2006 | + 45 days | Article II.7.2.b (ii) | 5
Report | Summary financial report | 31/12/2006 | + 45 days | Article II.7.2.b (iii) | 6
Report | Distribution of funds | 31/12/2006 | + 45 days | Article II.7.2.c | 7
Report | Supplementary reports | 31/12/2006 | + 45 days | Article II.7.2.d | 8
Cert | Audit Certificate per partner | 31/12/2006 | + 45 days | Article II.26 | 9
Report | 18 month implementation plan | 31/12/2006 | + 45 days | Article III.2 | 10
Report | JRC Share of Payment | 2006-12-31 | + 45 days | Article 9 (c) | 11
Review | Review of Year 3 | 1/4/2007 |  | Article II.7
Cluster | Cluster Meeting Year 4 | 1/6/2007 |  | Article 9.1
Payment | Advance next 18 months(Plan 4) | 2007-06-30 | 2800000 | Article 8.2.a Core | 1
Payment | Balance of year 3 | 2007-06-30 | -200000 | Article 8.2.b Core | 2
Payment | Advance 4-Balance Year 3 | 2007-06-30 | 2600000 | Article 8.2.b Core | 3
Report | Periodic activity report’ | 31/12/2007 | + 45 days | Article II.7.2.a | 1
Report | Dissemination +use plan’ | 31/12/2007 | + 45 days | Article II.7.2.a | 2
Report | Management report | 31/12/2007 | + 45 days | Article II.7.2.b | 3
Report | Justification of resources | 31/12/2007 | + 45 days | Article II.7.2.b (i) | 4
Report | Form C | 31/12/2007 | + 45 days | Article II.7.2.b (ii) | 5
Report | Summary financial report | 31/12/2007 | + 45 days | Article II.7.2.b (iii) | 6
Report | Distribution of funds | 31/12/2007 | + 45 days | Article II.7.2.c | 7
Report | Supplementary reports | 31/12/2007 | + 45 days | Article II.7.2.d | 8
Cert | Audit Certificate per partner | 31/12/2007 | + 45 days | Article II.26 | 9
Report | 18 mon. implementation plan | 31/12/2007 | + 45 days | Article III.2 | 10
Report | JRC Share of Payment | 2007-12-31 | + 45 days | Article 9 (c) | 11
Review | Review of Year 4 | 1/4/2008 |  | Article II.7
Cluster | Cluster Meeting Year 5 | 1/6/2008 |  | Article 9.1
Payment | Advance for last 12 months | 2008-06-30 | 2400000 | Article 8.2.a Core | 1
Payment | Balance of year 4 | 2008-06-30 | -800000 | Article 8.2.b Core | 2
Payment | Advance 5-Balance Year 4 | 2008-06-30 | 1600000 | Article 8.2.b Core | 3
Review | Final Review | 15/12/2008
Report | Periodic activity report’ | 31/12/2008 | + 45 days | Article II.7.2.a | 1
Final Report | Final activity report’ | 31/12/2008 | + 45 days | Article II.7.4.a | 1
Report | Dissemination+use plan’ | 31/12/2008 | + 45 days | Article II.7.2.a | 2
Final Report | Dissemination + use plan’ | 31/12/2008 | + 45 days | Article II.7.4.a | 2
Report | Management report | 31/12/2008 | + 45 days | Article II.7.2.b | 3
Final Report | Management report | 31/12/2008 | + 45 days | Article II.7.4.b | 3
Report | Justification of resources | 31/12/2008 | + 45 days | Article II.7.2.b (i) | 4
Report | Form C | 31/12/2008 | + 45 days | Article II.7.2.b (ii) | 5
Report | Summary financial report | 31/12/2008 | + 45 days | Article II.7.2.b (iii) | 6
Final Report | Summary financial report | 31/12/2008 | + 45 days | Article II.7.4.b (iii) | 6
Report | Distribution of funds | 31/12/2008 | + 45 days | Article II.7.2.c | 7
Report | Supplementary reports | 31/12/2008 | + 45 days | Article II.7.2.d | 8
Final Report | Supplementary reports | 31/12/2008 | + 45 days | Article II.7.4.c | 8
Cert | Audit Certificate per partner | 31/12/2008 | + 45 days | Article II.26 | 9
Cert | Audit Certificate per partner | 31/12/2008 | + 45 days | Article II.26 | 9
Report | 18 month implementation plan | 31/12/2008 | + 45 days | Article III.2 | 10
Report | 18 month implementation plan | 31/12/2008 | + 45 days | Article III.2 | 10
Report | JRC Share of Payment | 2008-12-31 | + 45 days | Article 9 (c) | 11
Payment | Final Payment | 2009-06-30 | 600000 | Article 8.2.a Core | 1
Report | Distribution of funds | 2009-06-30 | + 45 days | Article II.7.4.d | 7
Audit | End of Audit Period | 31/12/2011

## Payments
Title of Contract
| ACRONYM |  |  |  | EU Contribution
| Contract Number |  |  |  | €
| Start Date | 2004-01-01 | End Date | 2008-12-31 | 15000000 |  | Article 5 Core Contract | Article 5 Core Contract
| % Advance Payment (e.g. 80) |  |  |  | 80 | % |  | Article 4.2 Core Contract
| Period 1 | 2004-01-01 | to | 2004-12-31 | 3000000 |  | Table Annex 1 | Article 6 of Core Contract
| Period 2 | 2005-01-01 |  | 2005-12-31 | 4000000 |  | Table Annex 1 | Article 6 of Core Contract
| Period 3 | 2006-01-01 |  | 2006-12-31 | 3000000 |  | Table Annex 1 | Article 6 of Core Contract
| Period 4 | 2007-01-01 |  | 2007-12-31 | 2000000 |  |  | Article 6 of Core Contract
| Period 5 | 2008-01-01 |  | 2008-12-31 | 3000000 |  |  | Article 6 of Core Contract
| Mid - Term Review | 2006-01-15 | Date agree with Project Officer
| Number of Partners |  |  | 35
Advance Payment | Advance Payment 18 month plan (Plan 1) |  |  |  | 4000000 |  | 80% (Year 1+50% of year 2)
| Net Payment for Plan 1 |  |  |  |  | 4000000
End of Year 1 | Advance Payment 18 month plan (Plan 2) |  |  |  | 4400000 |  | 80% (Year 2+50% of year 3)
| Balance of Year 1 |  |  |  | -1000000 |  | Year 1-Advance Plan 1
| Net Payment for Plan 2 |  |  |  |  | 3400000
End of Year 2 | Advance Payment for 18 month (Plan 3) |  |  |  | 3200000 |  | 80% (Year 3+50% of year 4)
| Balance of Year 2 |  |  |  | -400000 |  | Year 2-Advance Plan 2
| Net Payment for Plan 3 |  |  |  |  | 2800000
End of Year 3 | Adavnce Payment for 18 month (Plan 4) |  |  |  | 2800000 |  | 80% (Year 4+50% of year 5)
| Balance of Year 3 |  |  |  | -200000 |  | Year 3-Advance Plan 3
| Net payment for Plan 4 |  |  |  |  | 2600000
End of Year 4 | Advance Payment for 12 month (Plan 5) |  |  |  | 2400000 |  | 80% (Year 5)
| Balance of Year 4 |  |  |  | -800000 |  | Year 4-Advance Plan 4
| Net Payment for Plan 5 |  |  |  |  | 1600000
End of Year 5 | Balance of Year 5 |  |  |  | 600000 |  | 20% of Year 5
| Net Final Payment |  |  |  |  | 600000 | Year 5-Advance Plan 5)
| Total Payments |  |  |  | 15000000 | 15000000