## Sheet1
Task | Description Months | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
1 | Development of Methodology | bar: 1 to 7
1.1 | Workshop on user needs | bar: 1
1.2 | Draft of methodology | bar: 2 to 6
1.3 | Evaluation of methodology | bar: 6 to 7
2 | Specification of Integrated System | bar: 1 to 14
2.1 | Inventory of resources in selected regions | bar: 1 to 2
2.2 | Review of existing facilities | bar: 2 to 4
2.3 | Specify technical developments required | bar: 4 to 6
2.4 | Impact analysis of different scenarios | bar: 6 to 9
2.5 | Prepare detailed business plans | bar: 9 to 14
3 | Feasibility Studies for each region
Review existing practices | bar: 1 to 3
Review technologies (state of the art) | bar: 1 to 6
Sensitivity analysis of scenarios | bar: 3 to 8
Report on most suitable options | bar: 8 to 17
4 | Project Management and Coordination
Dissemination of information: Workshops | bar: 7; 12; 18
Milestones and Deliverables
Guideline for methodology | bar: 4
Interim Reports | bar: 6; 12; 18
| Business Plans for four regions | 10: Draft; 16: Final
Public Workshop on results | bar: 18
Final Report | bar: 18